## Slide 1
Velti for Vodafone Campaign Management Process
Proprietary Notice
This material is proprietary to Velti and Affiliates. It contains trade secrets and confidential information which is solely the property of Velti and its Affiliates. This material shall not be used, reproduced, copied, disclosed, and transmitted, in whole or in part, without the express consent of Velti. © 2020 Velti. All rights reserved.

## Slide 2: TECHNICAL SET-UP
Velti is the trusted partner for Vodafone Germany when it’s about regular customer communication via SMS/MMS/Mobile Internet
Listed Supplier / VPA (Vodafone Procurement Agreement) with VPC (Vodafone Procurement Company) in Luxembourg
Direct connection to all relevant technical interfaces:
SMS-C/MMS-C connections (MM7/MM3)
File transfer interface via SFTP
DNS entry for easy-to-integrate mobile micro sites
Campaign Management Tool (CMT) which allows comfortable campaign approval processes
Individual content optimization for all mobile phones
Any kind of personalization possible
Device database to ensure that customers receive the content each single device requires (device-based content optimization)
Delivery notification (DLR) incl. retries
Reporting and campaign evaluation

## Slide 3: Process overview – Commercial
Velti
VPC
Accounting
Velti
1
Quotation / SOW
2
PO Allocation
Invoice
Payment
9
Campaign Manager
center@vodafone.com
6a
Content Delivery (ideally 3 - 5 days prior to broadcast)
5a
Campaign Enquiry
Internal communication process
Data Delivery (ideally about 2 days prior to broadcast)
RFQ via EVO Tool (BUY FROM model)
4a
3
Internal communication process
5b
6b
Content Optimization
Broadcast Preparation
(easybill)
Delivery Note
(easybill)
7
8
(easybill)
(taulia / Ariba)
(via Ariba)
(via taulia)
4b
PO Acceptance
Velti’s trading partner is VPC; OpCo contacts VPC and VPC contacts Velti to procure goods/services
4c
Create Project
(via Asana)
Notes: Kampagnen Anfrage vom Kunden (Telekom)
Erstellung eines KVA‘s von Velti/DWC
Bestätigung/Ablehnung des KVA‘s
?
Inhalt wird geliefert//Inhalt wird aufbereitet/verarbeitet
Daten werden geliefert (MSISDNs)//Versand wird vorbereitet
Rechnung wird gestellt
Rechnung wird bezahlt

## Slide 4: Process overview – Campaign Coordination
Creation of
MMS Preview
Campaign set-up
(DWC Toolbox)
Preview Link (approval process)
5.2
5.3
Feedback Vodafone
5.4
5a
Content delivery
Optimizations (if required)
Optimizations (if required)
Creation of Target
Formats & videos
Development
of Landing Page (if integrated)
Testing & QA
Test broadcast
Final approval
Test broadcast should be executed 2 days prior to launch (if requested)
In-time information of all involved departments for a better planning of the resources and compliance of timelines
5.5
5.6
5.8
5.7
5.9
Approval
Notes/remarks (non-release of Preview Link)
5.1
Updating Asana Project

## Slide 5: Process overview – broadcast Preparation
6a
Data delivery
(SFTP/Connect Direct)
Broadcast Preparation
Reporting (approx. after 14 days)
Data editing, converting and broadcast list creation (CSV file)
Upload Broadcast List
Template Creation (MMS and/or SMS )
Internal broadcast
External broadcast
Live broadcast
Evaluation of DLR (approx. after 5 days)
6.4
6.3c
6.5
6.1
6.3a
6.3b
Data is stored
in a database
Unique ID creation
(if requested)
6.2b
6.2a

## Slide 6: Organizational information
All campaigns are listed in the Campaign Calendar on a monthly basis iCloud Drive/Numbers/Kampagnenkalender ab 2020.numbers
Beyond that, the commercial status of each single campaign is listed in the Campaign Overview iCloud Drive/Numbers/Kampagnenkalender ab 2020.numbers

## Slide 7: Organizational information
Every campaign/project will be created in Asana (project management tool) https://app.asana.com/-/login

## Slide 8: Organizational information
Additionally, every campaign/project will be created in our Toolbox (Preview Link for approval process) https://internal.drwolfconsulting.de/login/